## Sheet1
Risk Matrix
| Negligible | Minor | Major | Hazardous | Catastrophic
Very unlikely | Low | Low | Low-medium | Medium | Medium
Unlikely | Low | Low | Low-medium | Medium | Medium-high
Moderate | Low | Low-medium | Medium | Medium-high | Medium-high
Likely | Low | Low-medium | Medium | Medium-high | High
Very likely | Low-medium | Medium | Medium-high | High | High
Number | Description | Effect | Response | Control Measure | Likelihood | Impact | Risk
1 | PC crashes | Some progress is lost | Use frequent commits | Mitigate | Unlikely | Minor | Low
2 | Github goes down | All commits are lost | Save everything locally | Accept | Very unlikely | Major | Low-medium
3 | Hyperfocus on tasks | Unhealthy, wasted time | Take short, frequent breaks | Mitigate | Likely | Minor | Low-medium
4 | Struggle with understanding task | Wasted time and effort, increased stress | Ask for help from trainer | Mitigate | Moderate | Minor | Low-medium
5 | Lose focus | Wasted time, become stressed | Use Kanban board, eliminate distractions | Mitigate | Very likely | Minor | Medium
6 | Fail to develop a working application | Failed project | Ask for help when needed, review all tasks | Mitigate | Unlikely | Catastrophic | Medium-high
7 | Struggle with unit testing | Incomplete project, application not tested | Ask for help, review previous work | Mitigate | Moderate | Major | Medium
8 | Poor posture | Neck and back pain | Stretch and take short breaks | Avoid | Moderate | Negligible | Low
9 | Implement feature that causes error in app | App not working | Create branches for all features | Mitigate | Likely | Minor | Low-medium
10 | Poorly written ReadMe file | User won't understand how to use app | Research other projects, ask questions | Mitigate | Likely | Negligible | Low
11 | Poor implementation of feature | App not working | Make frequent commits | Avoid | Likely | Minor | Low-medium
12 | Eye strain | Headaches, tiredness | Take short, frequent breaks | Mitigate | Likely | Negligible | Low